## Sheet1
Task # | Task Name | Resource | Task Notes | Duration | Start Date | Finish Date | Dependency | Outline Level
1 | Development | Davide, Mario, Moreno |  | 278g | 2017-01-09 08:00 | 2018-01-31 16:00 |  | 1
2 | Subcomponent development | Davide, Mario, Moreno |  | 30g | 2017-01-09 08:00 | 2017-02-17 16:00 |  | 2
3 | Subcomponent unit testing | Davide, Mario, Moreno |  | 40g | 2017-01-09 08:00 | 2017-03-03 16:00 |  | 2
4 | Subcomponent integration testing | Davide, Mario, Moreno |  | 10g | 2017-01-30 08:00 | 2017-02-10 16:00 |  | 2
5 | Component development | Davide, Mario, Moreno |  | 150g | 2017-02-13 08:00 | 2017-09-08 16:00 |  | 2
6 | Component unit testing | Davide, Mario, Moreno |  | 160g | 2017-02-13 08:00 | 2017-09-22 16:00 |  | 2
7 | Component integration testing | Davide, Mario, Moreno |  | 35g | 2017-08-21 08:00 | 2017-10-06 16:00 |  | 2
8 | Demo to client | Davide, Mario, Moreno |  | 1g | 2017-10-09 08:00 | 2017-10-09 16:00 |  | 2
| Deployment | Davide, Mario, Moreno |  | 4g | 2017-10-10 08:00 | 2017-10-13 16:00 |  | 2
11
Formulas:
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date]),"g")