## DD
Task # | Task Name | Resource | Task Notes | Duration | Start Date | Finish Date | Dependency | Outline Level
1 | DD | Davide, Mario, Moreno |  | 20g | 2016-11-14 08:00 | 2016-12-11 16:00 |  | 1
2 | Architecture draft | Davide, Mario, Moreno |  | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 |  | 2
3 | High level system view | Davide, Mario, Moreno |  | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 |  | 3
4 | Definition of system boundaries | Davide, Mario, Moreno |  | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 |  | 3
5 | Main architecture decisions | Davide, Mario, Moreno |  | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 |  | 3
6 | Meeting with clients | Davide, Mario, Moreno |  | 2g | 2016-11-17 08:00 | 2016-11-18 16:00 |  | 2
7 | Refining architecture choices | Davide, Mario, Moreno |  | 3g | 2016-11-21 08:00 | 2016-11-23 16:00 |  | 2
8 | Main components component diagram | Davide, Mario, Moreno |  | 3g | 2016-11-24 08:00 | 2016-11-28 16:00 |  | 2
9 | Components internal structure | Moreno |  | 2g | 2016-11-29 08:00 | 2016-11-30 16:00 |  | 2
10 | ER DB Model | Davide |  | 3g | 2016-11-29 08:00 | 2016-12-01 16:00 |  | 2
11 | Components external interfaces | Mario |  | 2g | 2016-11-29 08:00 | 2016-11-30 16:00 |  | 2
12 | Mapping components to goals | Mario, Moreno |  | 1g | 2016-12-01 08:00 | 2016-12-01 16:00 |  | 2
13 | Sequence diagrams | Davide, Moreno |  | 3g | 2016-12-02 08:00 | 2016-12-06 16:00 |  | 2
14 | Mockups | Mario |  | 3g | 2016-12-02 08:00 | 2016-12-06 16:00 |  | 2
15 | Deployment diagram | Mario, Moreno |  | 1g | 2016-12-07 08:00 | 2016-12-07 16:00 |  | 2
16 | Algorithms desing | Davide |  | 1g | 2016-12-07 08:00 | 2016-12-07 16:00 |  | 2
17 | Revision and requirement traceability | Davide, Mario, Moreno |  | 1g | 2016-12-09 08:00 | 2016-12-09 16:00 |  | 2
Formulas:
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date]),"g")