## RASD
N. attività | Nome attività | Risorsa | Commento | Durata | Data inizio | Data fine | Dipendenza | Livello struttura
1 | RASD | Davide, Mario, Moreno |  | 20g | 2016-10-16 08:00 | 2016-11-13 16:00 |  | 1
2 | Meetings with client | Davide, Mario, Moreno | All the resources will be present at the meeting | 3g | 2016-10-17 08:00 | 2016-10-19 16:00 |  | 2
3 | Identification of goals and stakeholders | Davide, Mario, Moreno |  | 1g | 2016-10-17 08:00 | 2016-10-17 16:00 |  | 3
4 | Requirements elicitation | Davide, Mario, Moreno |  | 2g | 2016-10-18 08:00 | 2016-10-19 16:00 |  | 3
5 | Modelization of the World and the Machine | Davide, Mario, Moreno | This part requires discussion and cooperation, hence it will be assigned to all the resources | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 |  | 2
6 | Identification of domain assumptions | Davide, Mario, Moreno |  | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 |  | 3
7 | Identification of system goals | Davide, Mario, Moreno |  | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 |  | 3
8 | Identification of requirements | Davide, Mario, Moreno |  | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 |  | 3
9 | Writing scenarios | Davide, Moreno |  | 1g | 2016-10-26 08:00 | 2016-10-26 16:00 |  | 2
10 | Identification of use cases | Moreno |  | 2g | 2016-10-27 08:00 | 2016-10-28 16:00 | 9 | 2
11 | Identification of needed data | Davide |  | 2g | 2016-10-27 08:00 | 2016-10-28 16:00 |  | 2
12 | Alloy model draft | Mario |  | 3g | 2016-10-26 08:00 | 2016-10-28 16:00 |  | 2
13 | In progress meeting with client | Davide, Mario, Moreno | All the resources will be present at the meeting | 1g | 2016-11-02 08:00 | 2016-11-02 16:00 |  | 2
14 | Document refinement | Davide, Mario, Moreno |  | 7g | 2016-11-03 08:00 | 2016-11-13 16:00 |  | 2
15 | Requirements refinement | Davide, Mario, Moreno | The requirements will be updated based on updates made in other parts of the document, during its developement | 7g | 2016-11-03 08:00 | 2016-11-13 16:00 |  | 3
16 | Data model refinement | Davide |  | 2g | 2016-11-03 08:00 | 2016-11-04 16:00 |  | 3
17 | Sequence diagrams for use cases | Moreno |  | 7g | 2016-11-03 08:00 | 2016-11-11 16:00 |  | 3
18 | Alloy modelization | Mario, Davide | Davide will start working on this activity in date 05/11/2016 | 7g | 2016-11-03 08:00 | 2016-11-11 16:00 |  | 3
Formulas:
Durata = CONCATENATE(NETWORKDAYS([Data inizio],[Data fine]),"g")