## Sheet1
Task # | Task Name | Resources | Duration | Start Date | Finish Date | Outline Level
1 | Mario |  | 40g | 2016-10-17 08:00 | 2016-12-11 16:00 | 1
2 | Meetings with client | Davide, Moreno | 3g | 2016-10-17 08:00 | 2016-10-19 16:00 | 2
3 | Identification of goals and stakeholders | Davide, Moreno | 1g | 2016-10-17 08:00 | 2016-10-17 16:00 | 3
4 | Requirements elicitation | Davide, Moreno | 2g | 2016-10-18 08:00 | 2016-10-19 16:00 | 3
5 | Modelization of the World and the Machine | Davide, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 2
6 | Identification of domain assumptions | Davide, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
7 | Identification of system goals | Davide, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
8 | Identification of requirements | Davide, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
9 | Alloy model draft |  | 3g | 2016-10-26 08:00 | 2016-10-28 16:00 | 2
10 | In progress meeting with client | Davide, Moreno | 1g | 2016-11-02 08:00 | 2016-11-02 16:00 | 2
11 | Document refinement | Davide, Moreno | 3g | 2016-11-03 08:00 | 2016-11-07 16:00 | 2
12 | Requirements refinement | Davide, Moreno | 3g | 2016-11-03 08:00 | 2016-11-07 16:00 | 3
14 | Alloy modelization |  | 3g | 2016-11-03 08:00 | 2016-11-07 16:00 | 3
13 | Document revision | Davide, Moreno | 4g | 2016-11-08 08:00 | 2016-11-11 16:00 | 2
15 | Architecture draft | Davide, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 2
16 | High level system view | Davide, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
17 | Definition of system boundaries | Davide, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
18 | Main architecture decisions | Davide, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
19 | Meeting with clients | Davide, Moreno | 1g | 2016-11-17 08:00 | 2016-11-17 16:00 | 2
20 | Refining architecture choices | Davide, Moreno | 2g | 2016-11-18 08:00 | 2016-11-21 16:00 | 2
21 | Main components component diagram | Davide, Moreno | 2g | 2016-11-22 08:00 | 2016-11-23 16:00 | 2
22 | Components external interfaces |  | 2g | 2016-11-24 08:00 | 2016-11-25 16:00 | 2
23 | Mapping components to goals | Moreno | 1g | 2016-11-28 08:00 | 2016-11-28 16:00 | 2
24 | Deployment diagram | Moreno | 1g | 2016-12-01 08:00 | 2016-12-01 16:00 | 2
25 | Revision and requirement traceability | Davide, Moreno | 1g | 2016-12-02 08:00 | 2016-12-02 16:00 | 2
26 | Integration test strategy | Davide, Moreno | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 | 2
27 | Definition of precedences | Davide, Moreno | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 | 2
28 | Sequence of components integration | Moreno | 2g | 2016-12-13 08:00 | 2016-12-14 16:00 | 2
29 | Program Drivers |  | 1g | 2016-12-15 08:00 | 2016-12-15 16:00 | 2
30 | Document revision | Davide, Moreno | 2g | 2016-12-16 08:00 | 2016-12-19 16:00 | 2
Formulas:
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date]),"g")