## Sheet1
Task # | Task Name | Resources | Duration | Start Date | Finish Date | Outline Level
1 | Davide |  | 46g | 2016-10-17 08:00 | 2016-12-19 16:00 | 1
2 | Meetings with client | Mario, Moreno | 3g | 2016-10-17 08:00 | 2016-10-19 16:00 | 2
3 | Identification of goals and stakeholders | Mario, Moreno | 1g | 2016-10-17 08:00 | 2016-10-17 16:00 | 3
4 | Requirements elicitation | Mario, Moreno | 2g | 2016-10-18 08:00 | 2016-10-19 16:00 | 3
5 | Modelization of the World and the Machine | Mario, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 2
6 | Identification of domain assumptions | Mario, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
7 | Identification of system goals | Mario, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
8 | Identification of requirements | Mario, Moreno | 4g | 2016-10-20 08:00 | 2016-10-25 16:00 | 3
9 | Writing scenarios | Moreno | 1g | 2016-10-26 08:00 | 2016-10-26 16:00 | 2
10 | Identification of needed data |  | 2g | 2016-10-27 08:00 | 2016-10-28 16:00 | 2
11 | Identification of use cases | Moreno | 1g | 2016-10-28 08:00 | 2016-10-28 16:00 | 2
12 | In progress meeting with client | Mario, Moreno | 1g | 2016-11-02 08:00 | 2016-11-02 16:00 | 2
13 | Document refinement | Mario, Moreno | 7g | 2016-11-03 08:00 | 2016-11-13 16:00 | 2
14 | Requirements refinement | Mario, Moreno | 3g | 2016-11-03 08:00 | 2016-11-07 16:00 | 3
15 | Data model refinement |  | 2g | 2016-11-03 08:00 | 2016-11-04 16:00 | 3
16 | Alloy modelization | Mario | 3g | 2016-11-03 08:00 | 2016-11-07 16:00 | 3
17 | Document revision | Mario, Moreno | 4g | 2016-11-08 08:00 | 2016-11-11 16:00 | 2
18 | Architecture draft | Mario, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 2
19 | High level system view | Mario, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
20 | Definition of system boundaries | Mario, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
21 | Main architecture decisions | Mario, Moreno | 3g | 2016-11-14 08:00 | 2016-11-16 16:00 | 3
22 | Meeting with clients | Mario, Moreno | 1g | 2016-11-17 08:00 | 2016-11-17 16:00 | 2
23 | Refining architecture choices | Mario, Moreno | 2g | 2016-11-18 08:00 | 2016-11-21 16:00 | 2
24 | Main components component diagram | Mario, Moreno | 2g | 2016-11-22 08:00 | 2016-11-23 16:00 | 2
25 | ER DB Model |  | 1g | 2016-11-24 08:00 | 2016-11-24 16:00 | 2
26 | Sequence diagrams | Moreno | 4g | 2016-11-25 08:00 | 2016-11-30 16:00 | 2
27 | Algorithms desing |  | 1g | 2016-12-01 08:00 | 2016-12-01 16:00 | 2
28 | Revision and requirement traceability | Mario, Moreno | 1g | 2016-12-02 08:00 | 2016-12-02 16:00 | 2
29 | Integration test strategy | Mario, Moreno | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 | 2
30 | Definition of precedences | Mario, Moreno | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 | 2
31 | Integration test description |  | 3g | 2016-12-13 08:00 | 2016-12-15 16:00 | 2
32 | Data required |  | 1g | 2016-12-16 08:00 | 2016-12-16 16:00 | 2
33 | Document revision | Mario, Moreno | 2g | 2016-12-16 08:00 | 2016-12-19 16:00 | 2
Formulas:
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date]),"g")