## Sheet1
Task # | Task Name | Resource | Task Notes | Duration | Start Date | Finish Date | Dependency | Outline Level
1 | ITPD | Davide, Mario, Moreno |  | 7g | 2016-12-12 08:00 | 2016-12-20 16:00 |  | 1
2 | Integration test strategy | Davide, Mario, Moreno |  | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 |  | 2
3 | Definition of precedences | Davide, Mario, Moreno |  | 1g | 2016-12-12 08:00 | 2016-12-12 16:00 |  | 2
4 | Sequence of components integration | Mario, Moreno |  | 2g | 2016-12-13 08:00 | 2016-12-14 16:00 |  | 2
5 | Program Drivers | Mario |  | 1g | 2016-12-15 08:00 | 2016-12-15 16:00 |  | 2
6 | Tools and equipment | Moreno |  | 1g | 2016-12-15 08:00 | 2016-12-15 16:00 |  | 2
7 | Integration test description | Davide |  | 3g | 2016-12-13 08:00 | 2016-12-15 16:00 |  | 2
8 | Data required | Davide |  | 1g | 2016-12-16 08:00 | 2016-12-16 16:00 |  | 2
9 | Document revision | Davide, Mario, Moreno | Davide will start working on this activity in date 19/12/2016 | 2g | 2016-12-16 08:00 | 2016-12-19 16:00 |  | 2
Formulas:
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date]),"g")
Duration = CONCATENATE(NETWORKDAYS([Start Date],[Finish Date],DATE(2016,12,8)),"g")